# Artist Support Grant Award Readiness Packet

Application 2673116

Prepared for Alphonzo “Zo” Roseboro
FAM Entertainment LLC and StarRise
Status date October 5, 2026

CURRENT STATUS Submitted and confirmed eligible

| Application fact | Current record |
| --- | --- |
| Applicant | Alphonzo Roseboro as an individual artist |
| Request | $3,000 |
| Project | Create and release four original songs |
| Submitted project period | January 15 through December 15, 2027 |
| Regional eligibility | Charlotte-area six-county Artist Support Grant region |
| Notification timing | By October 23, 2026, per applicant update email |

This is a post-submission readiness packet. It does not replace, revise, or duplicate the application already on file. Its purpose is to make the project ready for an award, a partial award, or a constructive follow-up if funding is not offered.

Immediate priority  Collect vendor estimates, verify work-sample credits and links, and prepare a clean grant record before the October 23 decision.

# Decision Readiness

On October 5, 2026, ASC program staff advised applicants that grant notifications will be issued by October 23, 2026. That applicant-specific update is the working decision date for this packet. The application was previously confirmed as successfully received and eligible.

## What to do before October 23

□ Save the record. Keep the submission confirmation, eligibility notice, October 5 update, and a copy of the submitted application together.

□ Price the approved scope. Obtain current written estimates for recording, engineering, mixing, mastering, producer or musician support, artwork, and photography.

□ Verify work samples. Confirm direct URLs, access permissions, dates, artistic role, and accurate writer, producer, performer, and ownership credits.

□ Prepare payment records. Use a separate project ledger and retain contracts, invoices, receipts, proof of payment, and final deliverables.

□ Wait for written terms. Do not assume a cost is grant-eligible or spend against the award until the award amount, approved period, and agreement terms are clear.

## Decision paths

| Result | First response | Operating move |
| --- | --- | --- |
| Full award | Acknowledge promptly and review every term | Confirm the $3,000 budget, eligible start date, credit language, and reporting requirements before spending |
| Partial award | Thank ASC and request written budget-revision guidance | Protect the recording and final-mix core; revise other lines only after approval |
| Not funded | Request panel feedback | Preserve the project, improve the narrative and samples, and reuse the packet for current individual-artist opportunities |

## Application control notes

Applicant identity. The grant application is in Alphonzo Roseboro’s name as an individual artist; keep award communications and grant records aligned to that applicant.

Residency record. Supporting records reference a current Cabarrus County residence and a Mecklenburg County permanent mailing address, both within the regional service area. Use the same truthful explanation and evidence if staff requests clarification.

Business separation. Treat FAM Entertainment LLC and StarRise as project context and support infrastructure, not as substitutes for the individual applicant named in the submission.

# Project Core

## Polished project narrative

Alphonzo “Zo” Roseboro will create, record, complete, and release a four-song project that brings together his R&B, soul, hip-hop, trap, and gospel influences. The project is designed to move four original songs from development through professional recording, engineering, mixing, mastering, and release preparation. Grant support will provide the technical and creative services needed to raise the sound quality of the work, strengthen Roseboro’s professional portfolio, and introduce the music to new listeners. Visual assets, including artwork and photography, will give the release a consistent public identity across streaming and promotional channels. The project is scheduled for January 15 through December 15, 2027, allowing time for pre-production, recording, post-production, visual development, distribution preparation, release, and documentation. The completed project will leave Roseboro with four finished masters, release-ready visual assets, and a stronger foundation for future performances, partnerships, and artist-development opportunities.

## Working artist bio

Alphonzo “Zo” Roseboro is a North Carolina singer, songwriter, producer, musician, and creative entrepreneur whose sound draws from R&B, soul, hip-hop, trap, and gospel. Music has been part of his life for years, and he has pursued his artistry with focused professional intent over the past two years. Roseboro writes and records original music, makes beats, plays instruments, and has gained live-performance experience through Connected TV opportunities. His released work is available on streaming platforms. Beyond his own music, he leads FAM Entertainment LLC and StarRise, an artist-focused platform built around development, visibility, collaboration, and opportunity. His current four-song project is the next step in strengthening his catalog, presenting his work at a higher technical level, and building lasting connections with listeners and creative partners.

## Intended outputs and outcomes

| Type | Committed result | Evidence to retain |
| --- | --- | --- |
| Creative output | Four original songs recorded, mixed, mastered, and prepared for release | Dated masters, stems, session notes, and credits |
| Visual output | Release artwork and artist photography | Final high-resolution files, invoice, and usage rights |
| Public reach | Four-song project made available through selected release channels | Live links, release dates, screenshots, and audience data |
| Career capacity | Stronger professional portfolio and repeatable production workflow | Updated bio, press assets, metadata, and project ledger |

Use the narrative and bio above as working copy. Before publishing them elsewhere, reconcile titles, credits, release channels, and any application-specific wording with the submitted record.

# Budget and Financial Controls

## Submitted request

| Budget line | Purpose | Amount | Share |
| --- | --- | --- | --- |
| Studio and engineering | Recording sessions and technical engineering | $1,200 | 40.0% |
| Mixing and mastering | Final mix balance, sonic polish, and release masters | $800 | 26.7% |
| Producer and musicians | Creative production and instrumental support | $600 | 20.0% |
| Artwork and photography | Release identity and promotional visuals | $400 | 13.3% |
| Total |  | $3,000 | 100.0% |

## Required record for every cost

□ Before commitment. Written quote or contract showing vendor, service, dates, scope, amount, and ownership or usage terms where relevant.

□ At payment. Invoice or receipt plus traceable proof of payment from the approved applicant or approved project account.

□ At delivery. Final files, session logs, approved credits, licenses or releases, and evidence that the service was completed.

□ In the ledger. Date, payee, budget category, description, amount, payment method, file location, and remaining balance.

□ For any change. Written approval when required before moving funds between categories or changing the funded scope.

## Recommended partial-award planning

These are contingency models only. Do not revise the approved budget without the funder’s written direction.

| Line | $2,250 model | $1,500 model | Priority logic |
| --- | --- | --- | --- |
| Studio and engineering | $1,000 | $700 | Protect clean source recordings |
| Mixing and mastering | $700 | $500 | Protect release-ready completion |
| Producer and musicians | $350 | $200 | Reduce sessions or scope |
| Artwork and photography | $200 | $100 | Use a lean visual package |
| Total | $2,250 | $1,500 | Requires approved revision |

# Working Execution Plan

This operating plan fits inside the submitted January 15 through December 15, 2027 project window. Reconcile it with the final award agreement and the exact production schedule before use.

| Phase | Target period | Work | Completion evidence |
| --- | --- | --- | --- |
| Pre-production | Jan 15–Feb 28 | Confirm four songs, arrangements, credits, collaborators, sessions, and vendor terms | Song list, split or credit notes, quotes, contracts, and calendar |
| Recording | Mar 1–Jun 30 | Track vocals and instruments; organize sessions and backups | Session files, logs, invoices, and rough mixes |
| Post-production | Jul 1–Sep 15 | Complete edits, mixes, revisions, mastering, and metadata | Approved mixes, masters, metadata, and payment record |
| Visual production | Sep 16–Oct 31 | Create artwork and photography; confirm usage rights | High-resolution assets, releases, invoice, and credits |
| Release preparation | Nov 1–Nov 30 | Deliver to distribution, build public assets, and schedule promotion | Delivery confirmation, release plan, links, and screenshots |
| Release and closeout | Dec 1–Dec 15 | Release, document results, reconcile budget, and prepare reporting file | Live links, final ledger, receipts, outcomes, and archive |

## Readiness calendar before the decision

| Date | Action | Finished when |
| --- | --- | --- |
| Oct 5–9 | Create one grant folder and save the application, confirmations, eligibility notice, and update email | The complete record opens without relying on inbox search |
| Oct 10–16 | Request written estimates that match all four submitted budget categories | Each line has at least one current, comparable estimate |
| Oct 17–22 | Verify work-sample links, roles, credits, and current artist bio | Every sample opens and every credit can be defended |
| Oct 23 | Review the notification and record the award amount, response deadline, terms, and next action | Decision and deadlines are entered in the tracker |
| Within 48 hours | Send the applicable response and ask only the questions needed to proceed | Receipt is acknowledged and requirements are clear |

# Work Samples and Grant File

## Work-sample control sheet

| Sample | Known submission context | Readiness action |
| --- | --- | --- |
| Smoke Weed | 2023 sample; Roseboro’s role identified as vocals. Submitted wording credited Fat Daddy as writer and producer. | Confirm the direct URL, access, exact title styling, all credits, and permission to reuse |
| Leaving | November 2012 sample included with the earlier application materials. | Confirm the direct URL or file, Roseboro’s artistic role, complete credits, and a concise relevance note |
| Current optional sample | A recent original recording or live performance can strengthen future packets if permitted. | Choose one strong, accessible link and document date, role, credits, and why it represents the current project |

## Recommended grant folder

| Folder | Contents |
| --- | --- |
| 01 Application Record | Submitted application, confirmation, application ID, and final narrative |
| 02 Eligibility and Updates | Eligibility notice, October 5 timing update, and later program correspondence |
| 03 Agreement | Award letter, contract, approved budget, amendments, and funder guidance |
| 04 Quotes and Contracts | Vendor estimates, scopes, session dates, rights terms, and signed agreements |
| 05 Invoices and Payments | Invoices, receipts, proof of payment, W-9s when required, and reconciled ledger |
| 06 Creative Deliverables | Sessions, stems, mixes, masters, artwork, photos, metadata, releases, and credits |
| 07 Promotion and Reach | Release links, screenshots, press, social posts, audience data, and partner evidence |
| 08 Reporting | Outcome notes, final budget, narrative draft, required acknowledgments, and submission receipt |

## Final pre-award checks

□ Identity and contact details match the submitted application. Correct any future correspondence through staff rather than creating conflicting records.

□ All work samples open without a login. Test on a second device and save stable backups where permitted.

□ Every collaborator has a documented role. Confirm rates, availability, credit, ownership, and delivery expectations.

□ Every budget line maps to a project output. Avoid unrelated StarRise, studio buildout, marketplace, or event expenses.

# Decision Response Drafts

## If fully funded

Subject  Artist Support Grant Application 2673116 Acceptance and Next Steps

Hello Iván,

Thank you for the Artist Support Grant notification and for the opportunity to support my four-song recording project. I am grateful for the award and confirm that I received the notice for application 2673116. I will review the award amount, agreement, approved project period, budget requirements, acknowledgment language, and reporting deadlines before making project commitments. Please let me know if any acceptance form, tax document, revised budget, or other action is required from me at this stage.

Best,
Alphonzo “Zo” Roseboro

## If partially funded

Subject  Artist Support Grant Application 2673116 Budget Revision

Hello Iván,

Thank you for the grant award and for supporting my four-song project. I am grateful to be selected. Before changing the submitted budget, I would like to confirm the required revision process and any limits on moving funds among recording and engineering, mixing and mastering, producer or musician support, and artwork or photography. Please share the deadline and format for an approved revised budget.

Best,
Alphonzo “Zo” Roseboro

## If not funded

Subject  Artist Support Grant Application 2673116 Feedback Request

Hello Iván,

Thank you for notifying me about the decision on application 2673116 and for the time invested in reviewing my project. I remain committed to completing the four-song release. If panel comments or a brief feedback conversation are available, I would appreciate guidance on the strongest elements of the proposal and the areas that would most improve a future application.

Best,
Alphonzo “Zo” Roseboro

# Backup Funding Screen

The best immediate strategy is to wait for the Artist Support Grant decision while making the current project execution-ready. Any backup opportunity should be screened against applicant type before time is spent on an application.

## Southern Artist Spotlight Grant

| Screen | Current finding | Meaning for Zo and StarRise |
| --- | --- | --- |
| Eligible applicant | Tax-exempt nonprofit or eligible government unit; the program does not accept a fiscal-agent substitute | Alphonzo as an individual and FAM Entertainment LLC as a for-profit are not direct applicants |
| Program model | An eligible presenter engages a Southern artist from the program roster for public activity and community engagement | This is a future host-partner pathway, not funding for the submitted four-song recording project |
| Readiness requirements | Organizational eligibility, current guidelines, eligible artist, UEI, cash match, timing, and public-program details must all be confirmed | Explore only when an eligible organization is willing to lead the application and project |

## Fallback sequence after October 23

1  Preserve the same project. Do not rebuild the concept from scratch. Keep the four-song scope, $3,000 budget logic, work samples, and production plan as the master file.

2  Use panel feedback. If the project is not funded, convert any reviewer comments into specific revisions to the narrative, samples, budget, or feasibility evidence.

3  Search for direct artist eligibility first. Prioritize current grants that accept individual North Carolina artists and allow recording, professional services, equipment, promotion, or project completion.

4  Use organization-only opportunities selectively. Pursue them only when a genuinely eligible nonprofit or government host leads the application and the program purpose matches the project.

5  Keep business costs separate. Do not shift unrelated StarRise platform, studio buildout, marketplace, or general operating expenses into an artist-project request.

## Program contact

| Contact | Details |
| --- | --- |
| Iván Garnica | Arts & Science Council regional contact |
| Email | ivan.garnica@artsandscience.org |
| Phone | 704-335-3036 |

# Source Record

Prepared October 5, 2026, from the applicant’s available submission record, grant correspondence, and the official program pages below.

| Source | Use in this packet |
| --- | --- |
| ASC Artist Support Grants https://artsandscience.org/artist-support-grants/ | Regional applicant guidance, eligible counties, funding categories, request ceiling, and cycle information |
| NC Arts Council Artist Support Grants https://www.ncarts.org/grants-resources/grants-dashboard/artist-support-grants | State program purpose and examples of eligible artist-development and project costs |
| ASC email Artist Support Grant Next Steps | Confirmation that application 2673116 was successfully received and eligible |
| ASC email Artist Support Grant Updates October 5, 2026 | Applicant-specific notice that decisions will be issued by October 23, 2026 |
| South Arts Southern Artist Spotlight Grant https://www.southarts.org/grants-opportunities/southern-artist-spotlight-grant | Backup eligibility screen for organization-led presentation activity |

## Packet status

| Component | Status | Next owner action |
| --- | --- | --- |
| Application record | Submitted and eligible | Retain the official copy and all email notices |
| Narrative and bio | Polished working copy | Confirm final public wording and credits |
| Budget | Matches the $3,000 request | Collect current written vendor estimates |
| Timeline | Award-ready working plan | Reconcile with agreement and vendor availability |
| Work samples | Two known samples documented | Add stable URLs and verified credits |
| Decision responses | Drafted | Send only the version that matches the official result |

End of packet